## SPRINT BACKLOG
SPRINT [NUMBER] BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
IN001 | As a estate centre agent I need to be able to see the fathers after tickets in their able todo these record. | Unistall standard points | R Rao | Completed | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Demo standard module and identify revised configuration. | R Rao | Completed |  | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remain true to promises made | R Rao | Completed |  | 5 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 7 | 0 | 0 | 4
IN002 | I need to make changes to existing system | Install the web application | A Shaikh | Completed | 48 | 0 | 0 | 5 | 7 | 2 | 8 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Apply customer branding | P Belote | Completed |  | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 9 | 0 | 0 | 0
IN003 | More the the number of fedbacks more we get to know those things | Install the more such web applications | S murto | Completed | 24 | 0 | 0 | 3 | 4 | 0 | 0 | 2 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0
|  | Integrate postcode plugin to contact page. | R Rao | Completed |  | 0 | 5 | 0 | 9 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0
|  | Install more such plugins | R Rao | Completed |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 4 | 0
|  | Complete any changes required from Demo | R Rao | Completed |  | 0 | 6 | 0 | 3 | 0 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
[5 empty] | 81 | 6 | 21 | 17 | 3 | 8 | 21 | 19 | 9 | 11 | 14 | 2 | 22 | 19 | 4 | 16

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates